## 2020-21 WORK PLAN
DER and Inverter-based Resources Subcommittee - Work Plan
Updated: January 28, 2021 |  | 2020 |  |  |  | 2021
| Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
DER Aggregation / Order 2222 - Active |  |  | Order issued |  |  |  | Compliance Due July 19th
Public Distribution Microgrids - Complete
Hybrid Resources - Active
Detailed Work Plan -- Public Distribution Microgrids | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 12.07.2020
Provide Education
Document Interests
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages | X
Build Consensus | X | X
Report Recommended Solutions to MIC/OC |  | X |  | X
Endorsement at MIC/OC |  |  |  |  | X
Detailed Work Plan -- Hybrid Resources | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 12.07.2020 | DIRS 1.07.2021 | DIRS 2.03.2021 | DIRS 3.03.2021 | DIRS 3.31.2021
Provide Education | X | X |  | X
Document Interests |  | X | X
Develop & Refine Design Components |  |  | X | X
Develop & Refine Component Options |  |  |  | X | X | X | X
Develop & Refine Solution Packages | [6 empty] | X | X | X
Build Consensus | [7 empty] | X | X
Report Recommended Solutions to MIC | [8 empty] | X
Detailed Work Plan -- DER Aggregation / Order 2222 Compliance | DIRS 08.03.2020 | DIRS 09.10.2020 | DIRS 10.02.2020 | DIRS 11.02.2020 | DIRS 11.24.2020 | DIRS 12.07.2020 | DIRS 1.07.2021 | DIRS 1.19.2021 | DIRS 2.03.2021 | DIRS 2.11.2021 | DIRS 3.03.2021 | DIRS 3.15.2021 | DIRS 3.31.2021
Overview of the Order |  |  | X | X
Education |  |  |  | X | X
Stakeholder Feedback and Discussion |  |  |  |  | X | X | X |  | X
EDC Coordination Workshop |  |  |  |  | X |  | X | X | X | X |  | X
Straw Proposal Discussion | [10 empty] | X