## SC #1
Generator and Merchant Transmission Project
Agreement Scope Change Form
[5 empty] | User Guide for completing this form: |  |  |  | To be filled in by Initiating Party
To be filled in by PJM
To be filled in by Project Developer or Transmission
Owner upon acknowledgement of scope change
| PJM Scope Change #: | [5 empty] | Scope Change Initiation Date:
| (Assigned by PJM) | [6 empty] | (Input by Initiating Party)
Initiating Party:
|  |  |  | (TO, PD, PJM) | [5 empty] | Contact Name
|  |  |  | TO = Transmission Owner |  |  |  |  | PD = Project Developer
Scope Change Type:
|  |  | Cost |  |  |  | Attachment Facilities / Queue Number:
|  |  | Schedule |  |  |  | Network Upgrade / Network Upgrade Number:
Other
Description / Technical Justification for Scope Change (or Potential Scope Change):
(attach additional documentation if necessary)
| Previous Approved Cost: | [7 empty] | Previous Approved Cost Date:
Scope Change Impact (projected):
|  | Cost: |  |  |  |  | (projected total cost increase / decrease)
|  | Schedule: |  |  |  |  | (revised in-service date) |  |  | Orig. In-Serv Date:
Other:
PJM Disposition on Scope Change Type:
|  | Existing Impact: |  |  |  | PJM Interconnection Planning Contact Name:
|  | New Impact: |  |  |  |  | Signature:
Date of PJM Disposition:
Change in Security Required :
|  |  | Yes |  | No |  | Revised Total Security Amount Required (if "Yes"):
Revised Expiration if Security is LOC:
Note: PJM disposition is an acknowledgement, and does not constitute an agreement or acceptance of the scope change.
Existing Impact:
PD/TO acknowledgement of Scope Change:
(note: for network upgrades, PJM will send this form to multiple Interconnection Customers, as required)
Queue No:
|  | Project Developer: | [7 empty] | Transmission Owner:
| PD: | [6 empty] | -1 | TO: |  |  | -1
| PD Contact: | [6 empty] | -2 | TO Contact: |  |  | -2
| Date of Acknowledgement: |  |  |  |  | -2 |  |  | Date of Acknowledgement: |  |  | -2
| PD Contact Signature: | [6 empty] | -3 | TO Contact |  |  | -3
Signature:
| PD or TO Instructions: |  | -1 | Type PD or TO Contact Company Name
|  |  | -2 | Type PD or TO Contact Name, and date of Acknowledgement, then email this form to PJM
|  |  | -3 | Print copy of this form, sign in appropriate PD or TO box, then either mail original copy or email a scanned copy to PJM
Note: The purpose of signing this form is to acknowledge the existence of a potential or actual scope change. This acknowledgement does not abrogate any
audit rights or dispute resolution rights after subsequent payment per PJM Tariff (OATT) requirements.
New Impact:
PJM to assign cost responsibility between PD and TO for New Impact.
|  |  | Baseline Upgrade | [7 empty] | New Baseline Upgrade Number:
|  |  | Revised agreement required | [7 empty] | New Network Upgrade Number:
Joint TO / Gen cost responsibility